## Exelare
Item # | Category | Issue Description | Recommendation / Clarification | Action Items / Next Steps | Estimate
1 | Data Migration | Additional environment and implementation steps documentation | cBizSoft (CS) will provide additional licenses for 3 months for this new environment and connect front-end application | Coordinate with Exelare to ensure the data migration is successful in the new play environment. CS to have a migration script ready for live version
2.1 | CV Management | Replace default CV (the CV given to the candidate) with the most recent document->type="CV". After finishing this, delete that document for this candidate. | Kris's comments: We will develop TSQL code, which will do the following: 1) If candidate has no CV docs, do nothing, 2) If candidate has CV doc(s), latest CV doc will become the Default CV (Resume for the candidate), then delete the Default CV (if any), then delete the CV doc . | Kris - need to give quote to the client | Need to give quote
2.2 | CV Management | Link the resumes automatically using uuFormNo, based on the files in a given folder, and file name will have "CV-uuFormNo-*" (Link the new resume, update the resumeText, do not parse the resume. Also make sure, the old resume becomes a document) | Kris's comments: We will develop a program which will be scheduled by the client using by windows schedular. This program will read a "folder", and process the resumes as per rules given by the client. After processing, move the resume to "Processed" sub-folder. | Kris - Have a separate call to review the details and the quotation How are the document and resume extracted? | Need to give quote
3 | Data Cleanup | 1. Delete all the documents (for consultants), with a Type value of "CV" except the most TWO recent documents of the given type ("CV") and associated links in the Links Table |  | Approved, do it now - 10/18/2016. Create TSQL to do this - give that to the client - also run it on ??? (try to give the count of deleted docs) - Vishnu write TSQL | 300
|  | 2. In Jobs->Status->subType, if the field value is "assignment completed", then delete certain statuses (list of status subtypes will be given by TKN) which belong to the given job and associated links in the Links Table. | Retain the following 10 status. Delete the rest 1. Availability Check (rename Vol Questionnaire) 2. Reference Check Completed 3. Selected 4. Insurance Certificate Issued 5. In Service 6. Preselected In Service 7. Completed 8. Preselected Completed 9. Vol EOA Completed 10. HI EOA Completed | Client will get back on this.
4 | User Interface | 1. Display Dates in views without time e.g. Birthdate | Clarifed to the client, that doing this may have impact filtering/sorting. Client said ignore this item
|  | 2. Set default columns widths so user sees maximum information without the need to scroll. | Users will set the desired widths - client's answer
|  | 3. Contrast between data labels and data – Need an option to adjust the look of the forms to make them more legible and provide user same experience as CBIZ - See screenshot comparing AS UI. All forms have same problem | Client will get back on this item
5 | Reminders Status Validation | 1. Blank Status Should not be allowed | Table: Reminders ApptType = 'status' and ApptSubType = '' | Kris's believes that we already have "must have" or "optional" for Reminders (Notes, etc) window. There could be a small customization fee for this, to modify "XAML" file(s). Kris will get back to client on this. | What ever quote might be (if any) Kris will give the quote
|  | 2. Blank Note Should not be allowed | Table: Reminders ApptType = 'note' and ApptSubType = ''
|  | 3. Number of opening should be numeric |  | Client said, they will change it to smallInt. If any issue, client will notify us.
|  | 4. Hold or Cancelled link should not be allowed if Assignment already in service | If a Status SubType is "a", do not allow a new Status, with Subtype "b". The client will the list of "a's" and corresponding "b's" | Kris - I am not sure if we have trigger's for Reminders, it not exist, let the client know. If exist, give the client the cost of writing the TSQL | Currently we do not have warning/error triggers for "Reminders" table.
5. No Volunteer status links should be allowed if Assignment is on Hold or Cancelled Status
6. Should not allow duplicate status links
6 | Training Demo | Training Demo - For Recruitment Team in the near future
Modified by Kris - 10/21/2016 6:32 AM

## 2.CV Management
2. CV Management and cleanup
1. Customized script to keep latest resumes (x2) only
Current and most recent
1. Keep the resume file - CV-1539299
2. Documents - Type ‘CV’
Keep the current and the most recent ones
e.g. Database\CV-1539299-201106061119571.pdf
Database\CV-1539299-201104151018491.pdf
Remove the remaining ones

## 4.User Interface
4. User Interface
Exelare | CBIZ

## 5.1 Blank Status
5.1. Blank Status not allowed
Reminders
ApptType = 'status' and ApptSubType = blank
Table: Reminders
ApptType = 'status' and ApptSubType = ''

## 5.2 Blank Note
5.2 Blank Notes not allowed
Reminders
ApptType = 'note' and ApptSubType = blank
Table: Reminders
ApptType = 'note' and ApptSubType = ''

## 5.3 No of Openings
5.3 No of openings should be numeric

## 5.4 Cancelling AS in service
5.4 Hold or Cancelled link should not be allowed if Assignment already in service

## 5.5 Linking Vol to cancelled AS
5.5 Assignment is cancelled but system allows volunteers to be linked

## 5.6 Dup Status links
5.6 Should not allow duplicate links